## Slide 1: What drives an employee leave the company? A study of Employee retention in Salifort Motors Project Proposal
Arpita Deb • 02.09.2023

## Slide 2: Goals
Expected delivery
September 10, 2023
Deliverables
A clean notebook with all the codes
Executive summary with summary and recommendations
A detailed report in GitHub

## Slide 3: Phase 1 - Planning
Business task
Identify the stakeholders
Define the business goal
Define the deliverables
Data
Collecting the data and other resources
Choosing tools and methodologies

## Slide 4: Phase 2 - Analyse
Tasks
Performing EDA using Python and Tableau
Perform descriptive statistics
Ethical considerations
Deliverables
Recording all the results in Jupyter Notebook

## Slide 5: Phase 3 - Construct
Tasks
Identify the data visualizations, machine learning models and other processes required
Define dependent and independent variables
Deliverables
Build the regression model
Record the results
Identify the possible solutions to problems faced
Create machine learning models

## Slide 6: Phase 4 - Execute
Tasks
Interpret the model results
Create a summary of the analysis
Define the limitations of the analysis and what can be done to improve the study
Deliverables
A clear and concise summary of the analysis
Propose recommendations along with limitations of the project, further research ideas, ethical considerations

## Slide 7: Attention areas
Regression analysis
Defining dependent and independent variables
Interpreting the model results
Machine Learning Models
Interpreting the model results
Choosing the right variables

## Slide 8: Schedule

## Slide 9
02.09.23
Create project proposal, collect resources, lay down the structure of report
03.09.23
Choose Python packages, perform EDA in Jupyter Notebook and Tableau
05.09.23
Logistic Regression Model and result interpretation
07.09.23
Decision Tree, Random Forest and XG Boost models and interpret the results
09.09.23
Write the summary, provide recommendations, final touches on the report